## Sheet1
Tasks Listed by their priority | Affiliated Engineers | Time Budget | Evaluation
Team Website | Ky/Ken/Elaine | week 1-3
GUI Design/graphic | Ken/Andy/Yvonne/Ky | Week 3 - 4
App/Game Core Functions | Ken/Yvonne/Elaine/Ky/Andy | week 5 - 8
Sprite/Game Graphics | Ken/Yvonne/Elaine | week 3 - 7
QA Testing | Ken/Yvonne/Elaine/Ky/Andy | week 8 - 10
Finalizing Phase | Ken/Yvonne/Elaine/Ky/Andy | Week 9-10
Facebook update | Ken/Yvonne/ | week 1-9
Twitter update | Ken/Yvonne | week 1-9